## Task List
# | FOS A to CCN | Assignee | Priority | Effort
1 | FOS A - Create FWB XML doc | Hitisoft | 1 | 5
2 | FOS A - Create FHL XML doc | Hitisoft | 2 | 5
4 | FOS A - Call CCN web Service to publish 2 doc | Hitisoft | 4 | 3
3 | FOS A - Construct CCN doc (sender, recipient, content etc) | Hitisoft | 3 | 3
5 | FOS A - Create web service to process acknowledgement - FMA - positive acknowledgement - FNA - negative acknowledgement - FSU - Shipment Status | Hitisoft | 5 | 5
Integrate FOS to CCN LINC Portal
1 | Provide CCN LINC Integration guideline document for FOS integration with LINC | CCN | 6
2 | FOS require to create Webservice for LINC to initiaise priori to redirecting to FOS (To be explain in detail later) | Hitisoft | 7 | 3
| 2i) Need to implement the IPRODUCT interface which consist of operation : Activate, Terminate, Suspend, ValidateAccess | Hitisoft | 8 | 5
3 | Once clear to redirect, LINC will redirect page to FOS, and pass in AccountID, CompanyID, SessionID, etc…(to be explain later) | CCN | 9
4 | FOS require consume LINC web service to set up session control in LINC , passing the SessionID | Hitisoft | 10 | 3 | Pending internal discussion
5 | and also periodically call LINC web service to check in so that the session does not expire in LINC | Hitisoft | 11 | 3
| Note: Class A and B agent accounts are created in CCN. |  |  | 35
Registration Process
1 | A1-----> B1, B2
2 | A1 register with LINC
3 | A1 indicate B1 & B2 are FOS company of A1
4 | CCN configure this manually in LINC
5 | B1 require to be registered company in LINC
6 | B1 subsribe to product FOS
7 | When B1 login to LINC, B1 can see FOS application icon in LINC
8 | B1 then click on the icon, and LINC will launch a FOSCompanyList page (CCN will create this page)
9 | At the page, it wil list A1 as one of the class A agent since previously A1 has indicated B1 as their customer
10 | B1 select the A1 in the list, LINC will redirect to A1 FOS main page (by Hitisoft)
Things to exchange
| Document Spec -> FWB, FHL, FSU , FMA, FNA, CCNDocument | From CCN
| Integration to LINC guideline document | From CCN
| CCN Service Bus inteface specification | From CCN
| Installation Guideline & System Specification | From HitiSoft
| Task List & process flow diagram | From CCN